## Sheet1
Tasks | Previous Cost (Hours) for all members | Revised Cost (Hours) for all members | Duration(Days)
Member Organisation | 1 | 1 | 2
Initial Planning | 2 | 2 | 1
Deliverable 0 | 4 | 4 | 1
Scheduling | 2 | 2 | 1
Resource Evaluation | 5 | 5 | 1
Technical Configuration | 3 | 3 | 2
Domain Model Design | 3 | 3 | 1
Architecture Planning | 5 | 5 | 2
Initial Architecture Design | 3 | 3 | 2
Database Setup | 24 | 24 | 1
Rapid Prototype | 24 | 24 | 1
Data Input | 15 | 15 | 1
Functional Requirements Planning | 10 | 10 | 3
Constraint planning | 5 | 5 | 1
Scoping | 5 | 5 | 1
Initial Front End Planning | 5 | 5 | 3
Estimation 1 | 1 | 1 | 1
Risk Planning 1 | 1 | 1 | 1
Deliverable 1 | 30 | 30 | 24
Architecture Design | 5 | 5 | 3
Front End Planning | 10 | 10 | 3
Front End Design | 10 | 15 | 4
Detailed Design | 10 | 10 | 2
Dynamic Design Scenarios | 20 | 25 | 4
Front End Prototype | 30 | 30 | 2
Estimation 2 | 1 | 1 | 1
Risk Planning 2 | 3 | 3 | 1
Deliverable 2 | 30 | 40 | 30
Implementation Planning | 15 | 20 | 4
Implementation | 40 | 50 | 5
Test Planning | 15 | 15 | 5
Testing | 30 | 45 | 2
Improvement | 15 | 30 | 2
Testing | 10 | 15 | 1
User Manual | 20 | 20 | 2
Final Cost Estimate | 2 | 2 | 1
Deliverable 3 | 40 | 60 | 20
Project Documentation | 80 | 90 | 7
Deliverable 4 | 15 | 20 | 10
TOTAL | 549 | 654 | 84