## Sheet1
Tasks | Project Estimate (Hours)
Member Organisation | 1
Initial Planning | 2
Deliverable 0 | 4
Scheduling | 2
Resource Evaluation | 5
Technical Configuration | 3
Domain Model Design | 3
Architecture Planning | 5
Initial Architecture Design | 3
Database Setup | 24
Rapid Prototype | 24
Data Input | 15
Functional Requirements Planning | 10
Constraint planning | 5
Scoping | 5
Initial Front End Planning | 5
Estimation 1 | 1
Risk Planning 1 | 1
Deliverable 1 | 30
Architecture Design | 5
Front End Planning | 10
Front End Design | 10
Detailed Design | 10
Dynamic Design Scenarios | 20
Front End Prototype | 30
Estimation 2 | 1
Risk Planning 2 | 3
Deliverable 2 | 30
Implementation Planning | 15
Implementation | 40
Test Planning | 15
Testing | 30
Improvement | 15
Testing | 10
User Manual | 20
Final Cost Estimate | 2
Deliverable 3 | 40
Project Documentation | 80
Deliverable 4 | 15
TOTAL | 549